## Sheet1
Project Number | Task Number | Project Name | Task Type | Task Name | Start Date of Task | Deadline of Task | Progress of Task | Planned Man-month | Actual Man-month | Planned vs Actual Ratio | Task Details | Task Type Number | Project Status | Progress of Progress | Start Date Project | Deadline of Project | Project Members | Project Description | Task History Number | Implemention Date | Implemention Time
P00001 | 1 | Building Customer Management System | Research | Market Research | 2024-07-16 | 2024-07-27 | 1 | 0.2 | 0.18 | 0.9 | Research for packages | T001 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 1 | 2024-07-16 | 8
P00001 | 1 | Building Customer Management System | Research | Market Research | 2024-07-16 | 2024-07-27 | 1 | 0.2 | 0.18 | 0.9 | Research for packages | T001 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 2 | 2024-07-24 | 8
P00001 | 1 | Building Customer Management System | Research | Market Research | 2024-07-16 | 2024-07-27 | 1 | 0.2 | 0.18 | 0.9 | Research for packages | T001 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 3 | 2024-07-26 | 8
P00001 | 1 | Building Customer Management System | Research | Market Research | 2024-07-16 | 2024-07-27 | 1 | 0.2 | 0.18 | 0.9 | Research for packages | T001 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 4 | 2024-07-27 | 2
P00001 | 1 | Building Customer Management System | Research | Market Research | 2024-07-16 | 2024-07-27 | 1 | 0.2 | 0.18 | 0.9 | Research for packages | T001 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 5 | 2024-07-27 | 2
P00001 | 2 | Building Customer Management System | Design | External Design | 2024-08-01 | 2024-08-12 | 0.2 | 1 | 0.15 | 0.15 |  | T002 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 1 | 2024-08-01 | 8
P00001 | 2 | Building Customer Management System | Design | External Design | 2024-08-01 | 2024-08-12 | 0.2 | 1 | 0.15 | 0.15 |  | T002 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 2 | 2024-08-01 | 8
P00001 | 2 | Building Customer Management System | Design | External Design | 2024-08-01 | 2024-08-12 | 0.2 | 1 | 0.15 | 0.15 |  | T002 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system | 3 | 2024-08-01 | 8
P00001 | 3 | Building Customer Management System | Others | Specification review | 2024-08-10 | 2024-08-10 | 0 | 0.05 | 0 |  | Design review | T009 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00001 | 4 | Building Customer Management System | Design | Internal Design | 2024-08-15 | 2024-08-26 | 0 | 1.5 | 0 |  |  | T003 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00002 | 1 | Building Sales Management System | Research | Market Research | 2024-07-01 | 2024-07-07 | 1 | 0.2 | 0.2 | 1 | Research for packages | T001 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 1 | 2024-07-01 | 8
P00002 | 1 | Building Sales Management System | Research | Market Research | 2024-07-01 | 2024-07-07 | 1 | 0.2 | 0.2 | 1 | Research for packages | T001 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 2 | 2024-07-02 | 8
P00002 | 1 | Building Sales Management System | Research | Market Research | 2024-07-01 | 2024-07-07 | 1 | 0.2 | 0.2 | 1 | Research for packages | T001 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 3 | 2024-07-05 | 8
P00002 | 1 | Building Sales Management System | Research | Market Research | 2024-07-01 | 2024-07-07 | 1 | 0.2 | 0.2 | 1 | Research for packages | T001 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 4 | 2024-07-06 | 8
P00003 | 1 | Repairing Human Resources System | Design | External Design | 2024-08-01 | 2024-08-02 | 1 | 0.1 | 0.1 | 1 | Identification of change points. Created revised external specifications. | T002 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system | 1 | 2024-08-01 | 8
P00003 | 1 | Repairing Human Resources System | Design | External Design | 2024-08-01 | 2024-08-02 | 1 | 0.1 | 0.1 | 1 | Identification of change points. Created revised external specifications. | T002 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system | 2 | 2024-08-02 | 8
P00003 | 2 | Repairing Human Resources System | Design | Internal Design | 2024-08-05 | 2024-08-09 | 0 | 0.2 | 0 |  | Addition of new specifications to Internal design documents | T003 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system
P00001 | 5 | Building Customer Management System | Others | Specification review | 2024-08-06 | 2024-08-15 | 0 | 0.05 | 0 |  | Design review | T009 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00003 | 3 | Repairing Human Resources System | Others | Specification review | 2024-08-09 | 2024-08-09 | 0 | 0.05 | 0 |  | Change specification review by leaders and clients | T009 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system
P00001 | 6 | Building Customer Management System | Implementation | Coding | 2024-08-15 | 2024-08-30 | 0 | 2 | 0 |  |  | T004 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 1 | 2024-07-12 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 2 | 2024-07-12 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 3 | 2024-07-13 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 4 | 2024-07-13 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 5 | 2024-07-14 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 6 | 2024-07-14 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 7 | 2024-07-15 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 8 | 2024-07-15 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 9 | 2024-07-16 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 10 | 2024-07-16 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 11 | 2024-07-17 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 12 | 2024-07-17 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system | 13 | 2024-07-20 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-20 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-21 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-21 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-22 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-22 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-23 | 8
P00002 | 2 | Building Sales Management System | Design | External Design | 2024-07-12 | 2024-07-23 | 1 | 1 | 1 | 1 |  | T002 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-23 | 8
P00003 | 4 | Repairing Human Resources System | Implementation | Coding | 2024-08-12 | 2024-08-15 | 0 | 0.4 | 0 |  |  | T004 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system
P00003 | 5 | Repairing Human Resources System | Testing | Integration testing | 2024-08-16 | 2024-08-20 | 0 | 0.1 | 0 |  |  | T006 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system
P00001 | 7 | Building Customer Management System | Others | Manual preparation | 2024-09-05 | 2024-10-01 | 0 | 0.5 | 0 |  |  | T008 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00003 | 6 | Repairing Human Resources System | Others | Manual preparation | 2024-08-20 | 2024-08-21 | 0 | 0.05 | 0 |  | Reflecting changes | T008 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system
P00003 | 7 | Repairing Human Resources System | Others | Release | 2024-08-22 | 2024-08-22 | 0 | 0.05 | 0 |  |  | T007 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system
P00003 | 8 | Repairing Human Resources System | Testing | Operational testing | 2024-08-22 | 2024-08-22 | 0 | 0.05 | 0 |  |  | T010 | In progress | 0 | 2024-08-01 | 2024-08-31 | James Johnson, Mary Hernandez | Partial renovations will be made in line with the new personnel system
P00002 | 3 | Building Sales Management System | Others | Specification review | 2024-07-26 | 2024-07-28 | 0.6 | 0.05 | 0.03 | 0.6 | Design review | T009 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-26 | 3
P00002 | 3 | Building Sales Management System | Others | Specification review | 2024-07-26 | 2024-07-28 | 0.6 | 0.05 | 0.03 | 0.6 | Design review | T009 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system |  | 2024-07-27 | 2
P00002 | 4 | Building Sales Management System | Design | Internal Design | 2024-07-27 | 2024-09-07 | 0 | 1.5 | 0 |  |  | T003 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system
P00001 | 8 | Building Customer Management System | Testing | Unit testing | 2024-09-19 | 2024-09-23 | 0 | 0.25 | 0 |  |  | T005 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00002 | 5 | Building Sales Management System | Others | Specification review | 2024-09-06 | 2024-09-06 | 0 | 0.05 | 0 |  | Design review | T009 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system
P00001 | 9 | Building Customer Management System | Testing | Integration testing | 2024-09-28 | 2024-10-01 | 0 | 0.25 | 0 |  |  | T006 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00002 | 6 | Building Sales Management System | Implementation | Coding | 2024-09-12 | 2024-09-30 | 0 | 2 | 0 |  |  | T004 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system
P00001 | 10 | Building Customer Management System | Others | Release | 2024-10-03 | 2024-10-05 | 0 | 0.1 | 0 |  |  | T007 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00002 | 7 | Building Sales Management System | Others | Manual preparation | 2024-09-17 | 2024-10-14 | 0 | 0.5 | 0 |  |  | T008 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system
P00001 | 11 | Building Customer Management System | Testing | Operational testing | 2024-10-06 | 2024-10-15 | 0 | 0.05 | 0 |  | Operation testing in business department | T010 | In progress | 0.2 | 2024-07-16 | 2024-09-30 | John Smith, William Martinez, Maria Garcia, Richard Brown | Renew and rebuild a customer management system
P00002 | 8 | Building Sales Management System | Testing | Unit testing | 2024-10-03 | 2024-10-07 | 0 | 0.25 | 0 |  |  | T005 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system
P00002 | 9 | Building Sales Management System | Testing | Integration testing | 2024-10-09 | 2024-10-14 | 0 | 0.25 | 0 |  |  | T006 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system
P00002 | 10 | Building Sales Management System | Others | Release | 2024-10-17 | 2024-10-17 | 0 | 0.1 | 0 |  |  | T007 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system
P00002 | 11 | Building Sales Management System | Testing | Operational testing | 2024-10-20 | 2024-10-21 | 0 | 0.05 | 0 |  | Operation testing in business department | T010 | In progress | 0.2 | 2024-07-01 | 2024-10-30 | Susan Lee, Nancy Walker, Matthew Green, Ashley Turner | Introducing a new sales management system